## Sheet1
TASK DEFINITION AND PLANING
TASK | Description | Start Date | End Date | Week
Project Scope | In this we will decide the future prospect of the app, discussing its possible impact on the customer | 2022-02-22 | 2022-02-27 | 1
Project Prototype | This week we will come up with a rough idea of the UI/UX of the Web app | 2022-03-01 | 2022-03-06 | 2
Coding Week 1 | This week we will start making the foundation of the web app using python and streamlit | 2022-03-08 | 2022-03-13 | 3
Coding Week 2 | This week we will start making the foundation of the web app using python and streamlit | 2022-03-15 | 2022-03-20 | 4
Bug fixing and first trial | We try the beta version of the web app and scrutinize the application followed by some bug fixing | 2022-03-22 | 2022-03-27 | 5
Final changes and suggestion(Deployment) | Last week we will deploy the web app and work on some suggestion provided by the beta users | 2022-03-29 | 2022-04-03 | 6

## Sheet2
TASK | Date | Position | Data Label
Project Scope | 2022-02-22 | 50 | 22-Feb-22 Project Scope
Project Prototype | 2022-03-01 | -50 | 1-Mar-22 Project Prototype
Coding Week 1 | 2022-03-08 | 80 | 8-Mar-22 Coding Week 1
Coding Week 2 | 2022-03-15 | -80 | 15-Mar-22 Coding Week 2
Bug fixing and first trial | 2022-03-22 | 50 | 22-Mar-22 Bug fixing and first trial
Final changes and suggestion(Deployment) | 2022-03-29 | -50 | 29-Mar-22 Final changes and suggestion(Deployment)